## Sheet1
S.No | PHASE | INPUT | ACTIVITIES | RESPONSIBILITY | OUTCOME
1 | Test Planning | Project Plan | Identify the Resources | Test Lead/Team Lead(70%) | Test Plan Document
| What to Test | Functional Requirements | Team Formation | Test Manager(30%)
| How to Test |  | Test Estimation
| When to Test |  | Preparation of Test Plan
Reviews on Test Plan
Test Plan Sign-Off
2 | Test Designing | Project Plan | Preparation of Test Scenarios | Test Lead/Team Lead(30%) | Test Cases Document
|  | Functional Requirements | Preparation of Test Cases | Test Engineers(30%) | Traceability Matrix
|  | Test Plan | Reviews on Test Cases
|  | Design Docs | Traceability Matrix
|  | Use Cases | Test Cases Sign-Off
3 | Test Execution | Functional Requirements | Executing Test Cases | Test Lead/ Team Lead(10%) | Status/Test Reports
|  | Test Plan | Preparation Of Test Report/Test Log | Test Engineers(90%)
|  | Test Cases | Identifying Defects
Build From Development Team
4 | Defect Reporting & Tracking | Test Cases | Preparation Of Defect Report | Test Lead/ Team Lead(10%) | Defect Report
|  | Test Reports/ Test Log | Reporting Defects To Developers | Test Engineers(90%)
5 | Test closure/ Sign-off | Test Reports | Analyzing Test Reports | Test Lead/ Test Manager(70%) | Test Summary Reports
|  | Defect Reports | Analyzing Bug Reporting | Test Engineer(30%)
Evaluating Exit Criteria